## 07.06.19
Daily Progress Report
JOB |  | Plant Civil Including Under Ground Civil Works.
Contractor |  | M/s N J Devani Builders Pvt.Ltd. | [6 empty] | Status as of |  | 07.06.2019
WO No. |  | 3SC/31311787 | [6 empty] | Project Name |  | HIIR - ETP Project
Sl. No. | Activity Description |  |  | UOM | Scope | Completed |  |  | Balance | % Completed | Remarks
[6 empty] | Upto Previous | Today | Total
A | Work Progress. (Scope only Equalization, Aeration Tank, Sludge tank, Drain pit, Secondary Clarifier, Chlorine Contact tank, DAF, Filtered effluent tank, Centrifuge Building, Chemical House, Pump foundation , Static Equipment, All Pipe rack and Battery limit column )
1 | Excavation
(a) | Soft Rock |  |  | Cum. | 2120 | 1954 | 10 | 1964 | 156 | 92.64%
(b) | Hard Rock |  |  | Cum. | 4520 | 3992 | 25 | 4017 | 503 | 88.87%
2 | PCC - Below Raft & Footings & Staircase footing |  |  | Cum. | 410 | 405.5 | 2 | 407.5 | 2.5 | 99.39%
3 | RCC Sub-Structure |  |  | Cum. | 1340 | 1292.5 | 5 | 1297.5 | 42.5 | 96.83%
4 | Backfilling
| Sand filling |  |  | Cum. | 2700 | 2700 | 0 | 2700 | 0 | 100%
| Soil Filling |  |  | Cum. | 1200 | 1200 | 0 | 1200 | 0 | 100%
5 | PCC - Below Grade Slab |  |  | Cum. | 110 | 110 | 0 | 110 | 0 | 100%
6 | Fixing Of Insert Plate |  |  | MT. | 13.7 | 13 | 0 | 13 | 0.7 | 94.89%
7 | Fixing Of Anchor Blot |  |  | MT. | 1.25 | 0.76 | 0 | 0.76 | 0.49 | 60.8%
8 | RCC Super-Structure |  |  | Cum. | 2275 | 2262 | 0 | 2262 | 13 | 99.43%
9 | Grouting |  |  | Cum. | 3 | 0.55 | 0 | 0.55 | 2.45 | 18.33%
10 | Faremate Hydrofillik Bar |  |  | Rmt. | 2700 | 2700 | 0 | 2700 | 0 | 100%
11 | AAC Block Masonry |  |  | Cum. | 42 | 42 | 0 | 42 | 0 | 100%
12 | 12mm thk. Smooth Faced Plaster |  |  | Sqmt. | 120 | 120 | 0 | 120 | 0 | 100%
13 | 20mm thk. Sand Faced Plaster |  |  | Sqmt. | 275 | 275 | 0 | 275 | 0 | 100%
14 | Surface Dressing |  |  | Sqmt. | 1250 | 0 | 0 | 0 | 1250 | 0%
15 | Concrete Paving |  |  | Sqmt. | 1250 | 0 | 0 | 0 | 1250 | 0%
16 | Paver Block 40mm thk. |  |  | Sqmt. | 0 | 0 | 0 | 0 | 0 | #DIV/0!
17 | Screed Concrete 95mm thk. |  |  | Sqmt. | 0 | 0 | 0 | 0 | 0 | #DIV/0!
18 | Acrylic Emulsion Paint |  |  | Sqmt. | 100 | 0 | 0 | 0 | 100 | 0%
19 | Anti Carbonation Paint |  |  | Sqmt. | 0 | 0 | 0 | 0 | 0 | #DIV/0!
20 | Shalitex Board 25mm thk. |  |  | Sqmt. | 40 | 40 | 0 | 40 | 0 | 100%
21 | PVC/UPVC Pipe Upot 250mm |  |  | Rmt. | 150 | 2.8 | 0 | 2.8 | 147.2 | 1.867%
22
23
24
25
26
B | Material Status |  |  | UOM | Min Qty. | Received |  |  | Consumed |  |  | Balance
[6 empty] | Upto Previous | Today | Total | Upto Previous | Today | Total
1 | Cement |  |  | MT. | 3 | 3 | 0 | 3
2 | Aggregate -10mm |  |  | MT. |  |  | 0 | 0
| -20mm |  |  | MT. |  |  | 0 | 0
3 | Sand |  |  | MT. |  |  | 0 | 0
| Filling sand |  |  | MT. | 5550 | 4189.42 | 0 | 4189.42
| River sand |  |  | MT. |  |  | 0 | 0
4 | Brick/Blocks |  |  | Nos. |  | 1050 | 0 | 1050
5 | Rubble |  |  | MT. |  |  | 0 | 0
6 | Reinforcement -
| 8mm |  |  | MT. | 20.641 | 18.45 | 0 | 18.45
| 10mm |  |  | MT. | 71.854 | 55.32 | 0 | 55.32
| 12mm |  |  | MT. | 75.285 | 81.87 | 0 | 81.87
| 16mm |  |  | MT. | 139.503 | 116.11 | 0 | 116.11 |  |  |  | 12.150 MT steel Issued From NJD to Niyti Engineering On dated 09/08/2018
| 20mm |  |  | MT. | 60.82 | 55.37 | 0 | 55.37
| 25mm |  |  | MT. | 0.5 | 0.462 | 0 | 0.462 |  |  |  | From Niyati Engineering pvt. ltd to NJD @t 04-9-18 ( total = 10 Rod)
| 32mm |  |  | MT. | 0 | 0 | 0 | 0
c | Manpower status
Category | Carpenter | Fitter | Helper | Mason | Welder | Gas Cutter | Scaffolder | Unskilled | Plumber |  |  | Total
Present at site | 3 | 3 | 8 | 3 |  |  |  | 17 | 4 |  |  | 38
c1 | Site Staff
Category | Site in charge | Planning/ Billing Engg. | Quality in charge | Site Engineer | Surveyour | Supervisor | HSE Person | Material/ Store Keeper | Electrician | Scaffolding Inspector |  | Total
Present at site | 1 | 1 | 1 | 1 |  | 2 | 1 | 2 | 1 |  |  | 10
D
P& M | Bar Cutting M/c | Bar Bending M/c | Auto Level | Total Station | Excavator | Water Tank | Tipper/ Tractor | Dewatering Pump | Mixer Machine | Vibrator | Stand Drill Machine | Earth Compactor
Available | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 |  | 4 | 1 | 1
E | Highlights/ Constraints
1
2
3
4
F | Building Work Activity
1 | Housekeeping work ,material shifting & cleaning work around ETP site
2 | Nipple grouting for FET tank and Flash Mixer Tank
3 | Excavation work in progress pipe rack 03
G
1
2

## 07.06.19 DD
Drawing Detail
JOB | Plant Civil Including Under Ground Civil Works.
Contractor | M/s N J Devani Builders Pvt.Ltd. | [7 empty] | Status as of |  | 07.06.2019
WO No. | 3SC/31311787 | [7 empty] | Project Name |  | HIIR - ETP Project
2019-06-01
Dwg.No. | Title | Category | Scope As per Drawing | Final Scope As per site | Complet | Balance | Weekly Plan 2ndweek | Weekly Achieve 2nd week | Monthly Plan | Monthly Achieve | Today | Remarks
- | - | - | A | B | C = C+H | D = B-C | E | F | G | H | I
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0004 (R2) | Equalization Tank | PCC Sub-Structure | 104 | 63 | 63 | 0 | [5 empty] | Completed as on dated 30/03/2019
|  | PCC Super-Structure |  | 53 | 53 | 0
|  | RCC Sub-Structure | 1680 | 436.54 | 436.54 | 0
|  | RCC Super-Structure |  | 1074.46 | 1074.46 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0005 (R1) | Aeration Tank | PCC Sub-Structure | 72 | 168 | 168 | 0 | [5 empty] | Completed as on dated 19/03/2019
|  | PCC Super-Structure |  | 46 | 46 | 0
|  | RCC Sub-Structure | 1170 | 420 | 420 | 0
|  | RCC Super-Structure |  | 853 | 853 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0006 (R0) | Secondery clarifier | PCC Sub-Structure |  | 35 | 35 | 0 | [5 empty] | Completed as on dated 05/01/2019
|  | RCC Sub-Structure |  | 67 | 67 | 0
|  | RCC Super-Structure |  | 60 | 60 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0008 (R1) | Sludge Tank | PCC Sub-Structure | 3.1 | 11 | 11 | 0 | [5 empty] | Completed as on dated 12/10/2018
|  | RCC Sub-Structure | 41 | 37 | 37 | 0
|  | RCC Super-Structure |  | 4 | 4 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0013 (R1) | Drain pit | PCC Sub-Structure | 4.25 | 26 | 26 | 0 | [5 empty] | Completed as on dated 17/01/2018
|  | RCC Sub-Structure | 51.7 | 41 | 41 | 0
|  | RCC Super-Structure |  | 12 | 12 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0010 (R1) | Chlorine Contect Tank | PCC Sub-Structure | 7 | 9 | 9 | 0 | [5 empty] | Completed as on dated 24/12/2018
|  | RCC Sub-Structure |  | 35 | 35 | 0
|  | RCC Super-Structure |  | 56 | 56 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0005 (R1) | Flocculation,DAF & Flash mixer | PCC Sub-Structure |  | 6 | 6 | 0 | [5 empty] | Completed as on date 14/4/2019
|  | RCC Sub-Structure |  | 11 | 11 | 0
|  | RCC Super-Structure |  | 93 | 93 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B02-0009 (R2) | Filtered effluent tank | PCC Sub-Structure |  | 10 | 10 | 0 | [5 empty] | Completed as on dated 12/02/2019
|  | RCC Sub-Structure |  | 32 | 32 | 0
|  | RCC Super-Structure |  | 64 | 64 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0012 (R1) | Centrifuge Building | PCC Sub-Structure |  | 9 | 9 | 0 | [5 empty] | completed as on dated 16-04-2019
|  | RCC Sub-Structure |  | 18 | 18 | 0
|  | RCC Super-Structure |  | 45 | 45 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0011 (R1) | Chemical House | PCC Sub-Structure | 34.3 | 41 | 41 | 0 | [5 empty] | Completed as on dated 16/04/2019
|  | RCC Sub-Structure | 124 | 45 | 45 | 0
|  | RCC Super-Structure |  | 77 | 77 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0014 (R1) | static equipment foundation | PCC Sub-Structure |  | 4 | 4 | 0 | [5 empty] | Completed as on dated 15/03/2019
|  | RCC Sub-Structure |  | 22 | 22 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0015 (R1) | Rotary Equipment foundation | PCC Sub-Structure |  | 11 | 11 | 0 | [5 empty] | Completed as on dated 16/04/2019
|  | RCC Sub-Structure |  | 105 | 105 | 0
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0016 (R0) | Pipe Rack - 03 | PCC Sub-Structure |  | 5 | 0 | 5 | 5 |  | 5
|  | RCC Sub-Structure |  | 13.5 | 0 | 13.5 | 9.5 |  | 13.5
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0032 (R1) | Pipe Rack - 02 | PCC Sub-Structure |  | 2 | 0 | 2 |  |  | 2
|  | RCC Sub-Structure |  | 12 | 0 | 12 |  |  | 12
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0034 (R0) | Pipe Rack - 04 | PCC Sub-Structure |  | 15 | 0 | 15 |  |  | 15
|  | RCC Sub-Structure |  | 12 | 0 | 12 |  |  | 12
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0036 (R1) | Pipe Rack - 06 | PCC Sub-Structure |  | 1 | 0.7 | 0.3 | [5 empty] | Complete as on dated 06/05/2019
|  | RCC Sub-Structure |  | 1.5 | 0.78 | 0.72
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0039 | Battery room to PLC room | PCC Sub-Structure |  | 4.7 | 4.7 | 0
|  | RCC Sub-Structure |  | 15 | 14.83 | 0.17 |  |  | 0.17
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0038 | Cable Tray Support Blower Bay (Aeration East Side) | PCC Sub-Structure |  | 15 | 12 | 3 |  | 2 | 3 | 2 | 2
|  | RCC Sub-Structure |  | 14 | 10.98 | 3.02 |  | 2 | 3.02 | 2 | 2
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0031 | Pipe Rack - 01 | PCC Sub-Structure |  | 6 | 0 | 6 | 6 |  | 6
|  | RCC Sub-Structure |  | 34 | 0 | 34 | 17 |  | 34
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0035 | Pipe Rack - 05 | PCC Sub-Structure |  | 3 | 0 | 3 | 3 |  | 3
|  | RCC Sub-Structure |  | 2.5 | 0 | 2.5 | 2.5 |  | 2.5
10111-4D8JTH-MS0042-TIN-D-00-TYT761-B05-0025 (R1) | Drain Trenches,Pathway & Access way | PCC Sub-Structure |  | 180 | 18 | 162 |  | 18 | 90 | 18
|  | RCC Sub-Structure |  | 375 | 3 | 372 | 50 | 3 | 265 | 3 | 3
Total |  |  |  | 4811.2 | 4164.99 | 646.21 | 93 | 25 | 466.19 | 25 | 7