## Progress Report Format
N.J.DEVANI BUILDERS PVT.LTD.-DTA O's & U's Substation Plant Progress Report
Report Date:=????? Progress Date:?????
SR.NO | DESCRIPTION | UOM | SCOPE | Comp Till Date | Balance | Engg. Front | Mat. Front | Seq Hold | Net Front | Day Progress Date:??? Plan vs Actual |  | PVA | April'19 PVA | Weekly Plan vs Actual |  |  |  |  | Remarks-Reason for Shortfall
[10 empty] | Plan | Actual |  |  | 2019-04-04 | 2019-04-11 | 2019-04-18 | 2019-04-25 | 2019-05-02
A | BELOW PLINTH
1 | Excavation-Soft Rock | Cum | 700 | 0 | 700 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
2 | Excavation -Hard Rock | Cum | 350 | 0 | 350 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
2 | ATT | Sqm | 550 | 0 | 550 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
3 | PCC Below Footing | Cum | 30 | 0 | 30 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
4 | RCC Footing | Cum | 215 | 0 | 215 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
5 | Pedestal | Cum | 15 | 0 | 15 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
6 | Back Filling up to GL | Cum | 650 | 0 | 650 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
7 | PCC Below Plinth Beam | Cum | 8 | 0 | 8 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
8 | RCC Plinth Beam | Cum | 40 | 0 | 40 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
9 | Grade Slab PCC | Cum | 33 | 0 | 33 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
10 | Grade Slab RCC | Cum | 65 | 0 | 65 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
B | GROUND FLOOR
1 | Ground Floor Column | Cum | 45 | 0 | 45 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
2 | Ground Floor Slab | Cum | 145 | 0 | 145 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
C | FIRST FLOOR
1 | First Floor Column | Cum | 45 | 0 | 45 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
2 | First Floor Slab | Cum | 145 | 0 | 145 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
3 | Terrace Floor pardi | Cum | 25 | 0 | 25 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
D | FNISHING WORK
1 | GF Masonry | Cum | 150 | 0 | 150 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
2 | GF Plaster | Sqm | 750 | 0 | 750 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
3 | FF Masonry | Cum | 110 | 0 | 110 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
4 | FF Plaster | Cum | 750 | 0 | 750 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
5 | GF Internal Paint | Cum | 750 | 0 | 750 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
6 | GF Anti carbonation Pain | Cum | 600 | 0 | 600 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
7 | FF Internal Paint | Cum | 750 | 0 | 750 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
8 | FF Anti carbonation Pain | Sqm | 600 | 0 | 600 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
9 | GF Plumbing | % | 100 | 0 | 100 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
10 | GF Flooring/Dado | Sqm | 180 | 0 | 180 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
11 | FF Flooring/Dado | Sqm | 120 | 0 | 120 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
12 | Flash Ceiling | Sqm | 200 | 0 | 200 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
13 | Flash Flooring | Sqm | 200 | 0 | 200 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
14 | Epoxy Coating | Sqm | 700 | 0 | 700 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
15 | External Plaster | Sqm | 1200 | 0 | 1200 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
16 | Screed Concrete | Sqm | 750 | 0 | 750 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
17 | Terrace Floor Menbeane | Sqm | 360 | 0 | 360 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
18 | GF plumbing fixtures | % | 100 | 0 | 100 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
19 | External Paint | Sqm | 1200 | 0 | 1200 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
20 | Area Grading & Cleaning work | % | 100 | 0 | 100 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0
21 | Resolution of Punch Point | % | 100 | 0 | 100 |  |  |  | 0 |  |  | P | 0
[12 empty] | A | 0

## Manpower
N.J.DEVANI BUILDERS PVT.LTD.-DTA O's & U's Substation Plant RAG Manpower Report
Date:????
DAILY MANPOWER REPORT
Category | Uom | Carpenter | Barbender | Scaffolder | Mason | Semi skilled | Unskilled | Fitter | Welder | Gas Cutter | Grinder | Helper | Rigger | Others | Electrician | Mechanic | Total | Remarks
R | Nos.
A | Nos.
G | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STAFF AVAILABLITY REPORT |  |  |  |  | STAFF AVAILABLITY REPORT
Category | Uom | Site Incharge | Execution-Civil | Execution-Mech. | HSE | Planning & DCC | Billing | QA/QC-Civil | QA/QC-Mech. | Electrical | P&M | Store | Acounts | Admin | Total | Remarks
R | Nos.
A | Nos.
G | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P&M Sheet
N.J.DEVANI BUILDERS PVT.LTD.-DTA O's & U's Substation Plant RAG P&M
Date:?????
Sr No. | Category | Unit | R | A | G | Remarks
1 | Crawler Crane - 270 T | EA |  |  | 0
2 | Crawler Crane - 180 T | EA |  |  | 0
3 | Crawler Crane - 101 - 150 T | EA |  |  | 0
4 | Crawler Crane Basic | EA |  |  | 0
5 | Tyre Mounted Crane - 75 T | EA |  |  | 0
6 | Hydra | EA |  |  | 0
7 | Manlifter | EA |  |  | 0
8 | Flat Bed Trailer | EA |  |  | 0
9 | Truck long Body | EA |  |  | 0
10 | Pick-up Van | EA |  |  | 0
11 | Water Tanker | EA |  |  | 0
12 | Air Compressor (CFM) | EA |  |  | 0
13 | Welding M/c | EA |  |  | 0

## Rain Log
RAIN LOG SHEET - DTA O's & U's Substation Plant
Sr. no. | Date | Start Time | Stop Time | Affected Working hours | Total Loss working hours | Remarks

## Site Constraint
N.J.DEVANI BUILDERS PVT.LTD.-DTA O's & U's Substation Constraints List
Date:??????
Sr. No. | Date | Constraint | Impact | Impact in days | Area | Manpower Assigned for the Work | Remarks